AVIS D’APPEL D'OFFRES PUBLIQUE No 010/ANCP /EZO/FY24

| A: Tous | Pour tout renseignement, écrivez à l’adresse ci-après : |
| --- | --- |
| De: WOLRD VISION DR CONGO Project : DRA/JR5 | Email: drc_procurments@wvi.org |
| Date Limite : 22/12/2023 | Nombre de pages incluant cette page : 20 |

Objet: Appel d’Offres des travaux d’Evaluation finale du projet

Messieurs/Mesdames,

Dans le cadre de la mise en œuvre du Projet ANCP exécute a Kalehe au Sud-kivu, World Vision DRC invite les entreprises du secteur de l’évaluations des projets à soumettre leur offre Technique et Financière à cet appel d’offres relatif à la réalisation des travaux de l’évaluation externe des activités réalisées dans le cadre de ce projet.

- World Vision DR Congo, au travers de son service de la chaine d’approvisionnement invite tous les potentiels Cabinets l’évaluations intéressés et remplissant les critères, à soumissionner en suivant les instructions ci-dessous ;

- Si vous êtes intéressé, veuillez envoyer par un mail aux adresses ci-haut, votre soumission (technique et financier) au plus tard le 09 Novembre.

L’objet du mail doit être obligatoirement AVIS D’APPEL D'OFFRES PUBLIQUE No 010/ANCP /EZO/FY24

- Offre Technique et Financière

Eléments Clé de l’Offre Technique :

- Lettre de soumission avec le cout total du marché ;

- Présentation de l’Entreprise ou de la Société ;

- CV et copie des Diplômes des personnes clés qui seront sur le Projet ;

- Méthodologie de travail ;

- Chronogramme/planning des activités ;

- La Liste des équipements de travail dont vous disposez ;

- 3 Références récentes des travaux similaires ; les expériences dans la zone d’intervention constituent un atout

- Offre Financière

  - Offre des Prix

  - Documents Administratifs et Fiscaux à jour :

    - Le RCCM, Registre Commercial et des Crédits Mobiliers

    - Identification Nationale

    - Numéro d’immatriculation CNSS accompagné la preuve de régularité des cotisations CNSS)

    - Certificat d’agrément aux ITPR

    - Le Numéro d’impôt

    - Attestation de la Situation Fiscale en cours de validité

  - Les Coordonnées Bancaires

  - Le délai de Validité de l’offre

  - Le délai de livraison

COMMENT POSTULER

- Pour postuler, envoyer un mail de manifestation d’intérêt à   drc_procurments@wvi.org tout en indiquant le numéro de l’offre.

- Votre offre (Technique et Financière) sera envoyée directement dans notre système coupa en travers le mail que vous recevrez entre le 22 et 25 décembre 2023. Les offres non envoyées par coupa ne seront pas prises en compte lors de l’évaluation technique.

N.B.:

- World Vision International se réserve le droit d'accepter ou de rejeter toute demande qui ne remplit pas les critères exigés et n'est pas tenue de donner les motifs de sa décision. Sauf les offres réunissant les conditions décrites ci-haut seront retenues et les soumissionnaires contactés pour des étapes suivantes ;

- Une mauvaise expérience avec World Vision lors des opportunités antérieures notamment des travaux mal faits, des retards horribles et non justifiés dans la mise en œuvre est une raison suffisante d’être exclu à concourir à ce marché !

Goma, le 15/ 12/ 2023

David MUNKLEY

Zonal Director

End-of-Project Evaluation Terms of Reference

Access to Quality Education in Kalehe, DRC

Project Number: C212819

World Vision World Vision DRC and

World Vision Australia

Contents

1	Project Summary	1

2	Project Description	2

3	Project Indicators	1

4	Intended Audience and Use	1

5	Evaluation Description	1

5.1	Objectives	1

5.2	Key Questions	1

6	Scope and Methodology	3

6.1	Overview	3

6.2	Quantitative data	4

6.3	Qualitative Data	4

Qualitative	4

7	Ethical and Technical Requirements	5

8	Roles and Responsibilities of Consultant/Evaluation Lead	5

8.1	Scope of work	5

8.2	Deliverables	5

8.3	Selection criteria	6

9	Roles and Responsibilities of Evaluation Participants	6

10	Assignment Conditions	8

11	Limitations	8

12	Schedule and timeframe	8

13	Budget	9

14	Instructions to bidders and evaluation criteria	10

15	Hiring Conditions and contractual requirements	10

16	Reference Documents	10

Glossary

Add and delete acronyms according to what is needed for your document.

AHADI		Associations of People with Disability for Integral Development

ANCP 		Australian-NGO Cooperation Programme

CoH		Channels of Hope

CHAT		Community Hope Action Team

CRS		(French acronym for) School Reintegration Centres

CVA		Citizen Voice and Action

DFAT		(Australian) Department of Foreign Affairs and Trade

DIVAS		Division of Social Affairs

DIVIGENRE	Division of Gender, Family & Children

DME		Design Monitoring and Evaluation

DPA		World Vision Development Programme Approach

DPO		Disabled Persons’ Organisation

DRC		Democratic Republic of Congo

FGD		Focus Group Discussion

GBV		Gender-Based Violence

EPST		Primary, Secondary and Vocational Education

IPP		Pronvincial Head Inspector for the EPST or MoE on provincial level

Inspool		Head Inspector for Primary schools on territory level

KII		Key Informant Interview

MoE		Ministry of Primary and Secondary Education

MoGCFA	Ministry of Gender, Children and Family Affairs

MoU		Memorandum of Understanding

M&E		Monitoring and Evaluation

NGO		Non-Government Organisation

PROVED	Head of the EPST on provincial level

PTA	    	Parent Teacher Association

RECOPE	Community Child Protection Networks

S4T		Savings for Transformation

SMC		School Management Committee

Sous-Proved	Head of educational subdivision (EPST on territorial level)

ToR		Terms of Reference

WASH		Water, Sanitation and Hygiene

WV		World Vision

WVA		World Vision Australia

WVDRC	World Vision Democratic Republic of Congo

# Project Summary

| Project Name | : Access to Quality Education in Kalehe, DRC |
| --- | --- |
| Project Number | : C212819 |
| Country and district(s) | : Democratic Republic of Congo, Kalehe Territory |
| Start date | : 1 July 2019 |
| End date | : 30 June 2024 |
| Total Project Budget | : USD4,425,754 |
| Project goal and outcomes | : Goal: Increase retention and attendance rates and improve learning outcomes for 15,660 girls and 16,200 boys in 30 primary schools in Kalehe, benefiting a total of 61,069 beneficiaries Outcome 1: Physical learning conditions in targeted schools are improved, on the basis of inclusion (gender and disability). Outcome 2: The quality of teaching learning and monitoring in targeted schools is improved. Outcome 3: The capacity of vulnerable households and communities to reduce barriers to education and promote quality education is strengthened. |
| Estimated Beneficiaries (Direct) Without disability; With disability; TOTAL. Men; Women; Boys (u18); Girls (u18); Men; Women; Boys (u18); Girls (u18). 10008; 12073; 16329; 16305; 1973; 1769; 1221; 1391; 61069. |
| Vulnerable groups included in the sample (if any) | : |

# Project Description

World Vision’s Access to Quality Education in Kalehe Territory, Democratic Republic of Congo (DRC) project aimed to increase school retention and attendance rates and improve learning outcomes in 30 primary schools, benefiting 61,069 people. The project aligned with DFAT's Partnerships for Recovery strategy, particularly the Economic Recovery, Health Security and Stability pillars.

The education system in the DRC faces many challenges, with 3.5 million primary-aged children not enrolled in school and only 67% of students completing Grade 6 (USAID, 2018). The project was designed to contribute to improved child education by increasing school access, retention and enrolment rates and improving learning outcomes. Working in conflict-affected areas, the project aimed to improve physical learning conditions and quality of teaching in target schools,and strengthen the capacity of vulnerable households to reduce barriers to quality education.

The project used World Vision’s Unlock Literacy model, underpinned by Citizen Voice and Action (CVA) and Savings for Transformation (S4T) to improve education accountability and support financial resilience in vulnerable families, plus Channels of Hope for Gender (CoHG) that mobilises faith leaders to address negative stereotypes affecting girls’ well-being, safety and education and MenCare.

The project worked in 30 schools to strengthen Parent-Teacher Associations (PTAs) and School Management Committees (SMCs) and connect them with Ministry of Education training and quality assurance functions to deliver high quality and safe learning environments. In communities, awareness raising campaigns re-inforced the importance of education for all children and adolescents, particularly girls and children with disabilities, and highlight gender-based barriers that disproportionally contribute to girls not attending school.

The project’s partnership with AHADI, a local Organisation of Persons with Disability (OPD),contributed to increased school attendance among children with disabilities through targeted community awareness and role modelling.

Project Outcomes:

Outcome 1:  Physical learning conditions in target schools are improved on the basis of inclusion (gender and disability). The project supports student access safe learning spaces in 30 schools including: ensuring water and sanitation infrastructure suits girls and children with disabilities, increase hygiene awareness and support SMCs and PTAs on effective management of safe, inclusive, conflict-sensitive and gender-responsive schools. Better learning environments are known to increase student attendance. The project aims for a 20% increase in student attendance by 2024.

Outcome 2:  The quality of teaching and learning in target schools is improved.

The project improves teaching capacity and gender-sensitivity of teachers, principals and other relevant duty-bearers, working closely with the Ministry of Education on training and coaching functions. 30 schools were supported with teacher training and learning materials. Social emotional learning was integrated in 30 schools’ learning environment to improve students’ competencies. Improving the quality of student education is intended to increase literacy scores by 15% in target schools by 2024.

Outcome 3:  The capacity of vulnerable households and communities to reduce barriers to education and promote quality education is strengthened. SMCs, PTAs, faith leaders and community stakeholders are trained and supported to champion gender equality and disability inclusion for enrolment and retention of girls and boys in school. Mixed media community awareness raising activities will cover gender equality, GBV, disability and social inclusion, student enrolment and retention, increasingly delivered by project participants (SMCs, PTAs, students). These activities will be focused on girls’ rights to education and protection and the importance of education for girls and children with disabilities. The introduction of S4T will help vulnerable families to reduce school dropouts due to lack of fee payment. Raising public awareness around the girls’ education is intended to increase enrolment and retention for girls by 20% by 2024.

# Project Indicators

Embed the LEAP logframe/M&E Plan here, and/or summarise the logframe statements and accompanying indicators that you expect to be measured by this evaluation.

| Coded | Results | Indicators | Baseline | Midline |
| --- | --- | --- | --- | --- |
| A. | Global objective: Increase retention and attendance rates and improve learning outcomes for 15,660 girls and 16,200 boys in 30 primary school in Kalehe, benefiting a total of 54,000 beneficiaries. |  |  |  |
| A1. | % of children currently enrolled in and attending a structured learning institution (age range 6 - 17) | Gross enrollment rate | - | 87.5% |
| A2. | The generation's percentage of children entering the first year at the same time and reaching the end of the cycle by redoubling or not | School retention rate | 61% | 52.6% |
| A3. | % of children in Grade 3 who can read a Grade 3 level passage | % of children in Grade 3 who can read a Grade 3 level passage and correctly answer at least of fact retrieval questions. | 23% | 36.8% |
| A4. | % Parents or caregivers with educational aspirations for their children (girls and boys). | % Parents or caregivers with educational aspirations for their children (girls and boys). | 88% | 88.8% |
| A5. | % Households reporting good social cohesion. | % Households reporting good social cohesion. | 32% | 91.2% |
| B. | Outcome I: Physical learning conditions in targeted schools are improved on the basis of inclusion (gender and disability) |  |  |  |
| B1. |  | % target schools meeting policy standards (or similar) that have been selected and agreed. | 0% | 36.8% |
| B2. |  | % target schools with a basic water source | 3% | 64.2% |
| B3. |  | % target schools with basic sanitation facilities. | 32% | 82.6% |
| B4. |  | % target schools with adequate menstrual hygiene facilities in place. | 0% | 50.2% |
| B5. |  | % of Grade 1–3 Unlock Literacy classrooms with print-rich environments | 0% | 76% |
| C. | Outcome II: The quality of teaching, learning and monitoring in targeted schools is improved |  |  |  |
| C1. |  | % Unlock Literacy trained teachers utilizing skills acquired to teach reading | 0% | 67.6% |
| C2. |  | % of pupils able to use numbers and basic arithmetic operations | 18% | 44.1% |
| C3. |  | % children who perceive that their school offers good learning and teaching environment | 58% | 62% |
| C4. |  | % children at CSR who go on to attend school regularly | 0% |  |
| C5 |  | % children reporting their schools treat them fairly (THIS INDICATOR WAS NOT MEASURED AT MIDTERM) | 20% | 0% |
| C6 |  | % of girls and boy who have demonstrated integration SEL competencies (THIS INDICATOR WAS NOT MEASURED AT MIDTERM) | 9% | 0% |
| C7 |  | Percentage of teachers practicing at least three of 5 SEL skills into their teaching routines (THIS INDICATOR WAS NOT MEASURED AT MIDTERM). | 5% | 0% |
| D. | Outcome III: The capacity of vulnerable households and communities to reduce barriers to education and promote quality education is strengthened. |  |  |  |
| D1. |  | % of households with a positive perception of inclusive education. | 63% | 98.1% |
| D2. |  | % of households where one or more adults are earning an income. | 43% | 41.2% |
| D3. |  | % of households able to pay for their children's basic education. | 37% | 57.5% |
| D4. |  | % of households aware of child protection mechanisms in place. | 57% | 85.2% |
| D5. |  | % of students declaring that they apply covid-19 prevention measures | 81% | 100% |
| D6 |  | Proportion of parents/guardians actively participating and supporting their children’s literacy development (THIS INDICATOR WAS NOT MEASURED AT MIDTERM) | 29% | 0% |
| D7 |  | Proportion of children with educational aspirations for themselves (THIS INDICATOR WAS NOT MEASURED AT MIDTERM) | 80% | 0% |

# Intended Audience and Use

| Intended Audience | Communication Method | Expected Use |
| --- | --- | --- |
| Community leaders | Reflection Meetings, Close Out processes | Community Level Planning for current and future initiatives |
| Project Staff | Evaluation Report | Design and redesign of similar future projects |
| Government Stakeholders (PROVED, IPP, Sous-Proved, DIVIGENRE, DIVAS) | Summary – Fact Sheet | Identify and support from a policy perspective the gaps and opportunities presented |
| WVDRC National Office | Evaluation Report | Design and redesign of similar ongoing and future projects |
| WV Australia Support Office | Evaluation Report | Design and redesign of similar ongoing and future projects |
| Donors | Evaluation Report | Refine priorities for similar project |
| Humanitarian and Development Community | Summary Document | Learning and application of best practices |

# Evaluation Description

## Objectives

- Assess the relevance and appropriateness of the project as measured by its ability to meet the needs of the affected population.

- Assess the effectiveness of the project as measured by the achievement of outcomes.

- Establish the extent to which the implementation of the project was efficient in terms of WVDRC´s systems, processes and structure

- Identify the negative and positive impacts that resulting from implementation of the project.

- Establish the extent to which project results will be sustainable after the transition from the project, as measured by the status of sustainability factors

- Recommend possible methods and approaches that might work for similar future programming based on identified best practices and lessons learned from the implementation of the ANCP project.

## Key Questions

Below are the key questions the evaluation will explore as informed by the stated evaluation objectives in 5.1 above.

| Objective | Key Questions |
| --- | --- |
| Objective 1 Assess the relevance and appropriateness of the project as measured by its ability to meet the needs of the affected population. | To what extent did the project address the needs of the most vulnerable (as defined in the project design) in the affected community? Pay particular attention to the marginalized groups like girls, women and people with disabilities. |
|  | How timely was the intervention and was it targeted to the right groups? Are there any new dimensions regarding timelines after the Covid 19 period? |
|  | How efficient was the targeting and beneficiary selection? |
| Objective 2 Assess the effectiveness of the project as measured by the achievement of outcomes. | Did the project achieve its outcomes as defined in the perfomance management framework? Specifically, were the learning outcomes of numeracy and literacy achieved? |
|  | What factors led to the achievement (or lack) of the project outcomes? |
|  | Were the approaches and models used by WVDRC, including . GESI actions, in project implementation suitable for the context? - Unlock literacy - Social Emotional Learning - Citizen Voice and Action (CVA) - S4T - Mencare - Channels of Hope – Gender |
|  | Were there any adaptations that were made for the project? To what extent were they informed by the context and beneficiary needs? Did the learning from the mid-term review inform the implementation of the project for better outcomes achievement? What were the results like? |
| Objective 3 Establish the extent to which the implementation of the project was efficient in terms of WVDRC´s systems, processes and structure | Was the project implemented in the agreed timelines and within the budget? |
|  | Were the most cost efficient approaches considered in project implementation? |
|  | How supportive were WVDRC systems and processes in terms of ensuring efficient project implementation (administration, procurement, P&C) etc |
| Objective 4: Identify the negative and positive impacts that resulting from implementation of the project. | What difference has the project made? What is the impact of the project interventions on school enrolment, retention and learning outcomes for girls and boys in Kalemie? (Project Theory of Change Test) |
|  | Were there any negative or positive impacts resulting from the project? What factors contributed to these? |
|  | What is the impact of the project interventions in addressing socio-cultural, economic and systemic barriers to education (response factors at individual, family, community and societal levels)? a. What is the impact of the project interventions to bring about behavioral change on the affected population and change harmful gender norms (early marriage, attitude towards girls' education, low value and support of girls) at individual, family and community level and increase the girls’ agency? b. What is the impact of the project interventions on creating access to education, improving education systems (e.g. policies, strategies, learning environments/spaces) and the capacity of teachers (knowledge, skills and attitude)? c. What is the impact of the project interventions on changing perceptions and behaviours of people in the affected community towards people with disabilities and on their general access to services (including physical)? d. Are there any positive impacts coming out of the implementation of the ANCP intervention (illustrate using at least 3 success stories captured during the evaluation –ensure consent from interviewees) e. What are the girl specific impacts of this intervention and at what level did these occur (household or institutional) and with which actors (caregivers - mothers, fathers, teachers, etc) f. How did the environment hazards impact the project and how anticipative was the project |
| Objective 5 Establish the extent to which project results will be sustainable after the transition from the project, as measured by the status of sustainability factors | Was the project deliberate to empower local structures (schools, RECOPE, community leadership, OPDs, other local NGOs, etc.) to manage their own development without WVDRC support? |
|  | What evidence is there that the results of the project will continue when the implementation of the project stops? |
|  | Which results/initiatives seem to be the most successful or have capacity to sustain after project closure? Which project structures have the most lasting impact, e.g. women S4T groups, fathers groups, COPA, COGEs, children governments, girls clubs and reading clubs etc. |
| Objective 6 Recommend possible methods and approaches that might work for similar future programming based on identified best practices and lessons learned from the implementation of the ANCP project. | What are the key best practices and lessons learned from the implementation of the ANCP project? How best can future interventions, including school infrastructure habitation /constructions &child protection, address environmental and climate related hazards throughout project cycle |
|  | How could the WVDRC and its partners implement a similar project in the future? |

# Scope and Methodology

## Overview

The evaluation is a summative one, which assesses all the outcomes from the implementation of the entire project. It is atime series design, comparing baseline, mid-term and end of project evaluation indicator performance. This therefore requires a robust methodology that combines both qualitative and quantitative methodologies.

## Quantitative data

The collection of quantitative data, will be done through a questionnaire established on the basis of the various indicators of results (OUTCOME) and change (IMPACT) that ensures the maintenance of the MTR methodology.

To find the households to be surveyed during these surveys, a sample size based on the Raosoft formulabelow will be used:

N =NxN-1E2 +x;

x= Zc1002 r100-r

and E=Sqrt[(N-n)x/n(N-1)]

r = the response fraction of interest;

Z(c/100) = critical value for the confidence level.

Z= 95%: Confidence level

E=5%: margin error

Two quantitative surveys will be conducted among the beneficiaries of the project's actions:

- STAR – this will target 3rd grade students and will maintain the midterm evaluation sample sizes. The STAR tool (using Tangerine) will assess the children’s proficiency in reading and arithmetic. The survey will purposively aim to also include at least 5% of children with disabilitys defined by the Washington Disability criteria.

- Quantitative survey tool (youths, teachers and community members) – this will target the different stakeholder groups and explore their perceptions on the implementation and success of the projects based on the key evaluation. Below is the sampling sizes adopted for each of the groups during the mid-term evaluation for the quantitative study. It will be important to maintain this for comparison purposes. In all the groups targeted, the study aims to reach 50% female participants though this may not be possible for the teacher survey where in some cases the male teachers dominate and there is no gender parity.

| No. | Categories of direct beneficiaries | Sample |
| --- | --- | --- |
| 1 | 3rd grade students (STAR survey) | 461 |
| 2 | Youth | 120 |
| 3 | Teacher | 180 |
| 4 | Community member households | 351 |
| Total |  | 1112 |

## Qualitative Data

## Qualitative

The evaluation is expected to maintain the key participants reached by the qualitative survey in the MTR to ensure consistency and comparability. The MTR documentation will be shared with the potential consultants upon request.

- Focus Group Discussions – the survey will target the key groups reached by the ANCP Kalemie project and carry out discussions with them based on the evaluation criteria and questions. The groups targetd at MTR include community members, members of S4T groups, teachers, parents of children living with disabilities, headmasters, book club facilitators and other key actors linked to the project, in particular.

- Key Informant Interviews – with staff, community leaders, state technical services, social affairs, EPST, local chiefs, etc. For consistency and comparability, the MTR sampling procedure will be followed.

# Ethical and Technical Requirements

The survey team must subscribe to the respect of the ethical rules and various other relevant policies of World-Vision. This step will be done through signing of the contract in connection with this evaluation mission. These are specifically the Code of Conduct for Suppliers, the letter of declaration of conflicts of interest, Safeguarding Policy & Acknowledgment Statement, the Protocol on anti-corruption and anti-fraud. In addition, during the implementation of our activities in the field, the consent of the persons interviewed and/or the guardian of the children must be obtained. The successful Consultant will be expected to address these issues (including during training of enumerators) as part of their Inception Report.

The consultant should ensure that all data from the survey is treated with strict confidentiality throughout the data collection, management and analysis process. All efforts should be taken to ensure that the participants in the survey are aware of the intended use of the data and the safeguarding measures in place to protect the data

# Roles and Responsibilities of Consultant/Evaluation Lead

## Scope of work

- The consultant must carefully read the ToR and develop a sound technical and financial proposal for the assignment.

- Must ensure that tool development and refinement of methods takes into cognisance the different groups targeted by the project, including the most vulnerable ones. The consultant has to put in place concrete measures to ensure the evaluation product is representative of all the voices.

- The inception report must respond to all issues raised in this ToR including how the evaluation will address the key evaluation questions

- Consultant is responsible for ensuring data quality through intensive training with the data collection and follow up measures through both physical measures and the utilisation of technology for data quality.

- The consultant must ensure that all data collected will be utilised and that all indicators have been properly mapped.

- Adequate measures for data management throughout the evaluation must be instituted for both quantitative and qualitative data.

## Deliverables

The consultant must deliver:

- An Inception Report using the embedded template

- Refined tools as part of the Inception Report

- A complete first draft report using the embedded template;

- A second to a third draft report using the embedded template;

- Submit the final evaluation report.

- a Final Report using the embedded template

- Worth noting that the Consultant will have presentation on collected data prior to first draft report

There may be other deliverables depending on what you have included in Section 8.1.

The following tools will be used to review and approve the final report.

The following tool will be used to assess the quality of the final report.   The score will not affect approval but consultants should aim to score highly according to each of the criteria as a way of maximising the quality of the report.

## Selection criteria

| Element | Score |
| --- | --- |
| Minimum of 5-10 years of experience in conducting studies, collecting data and producing qualitative and mixed-methods research reports, preferably for international non-profit organizations or multilateral agencies, including studies in education, child protection, youth empowerment, vocational training and related fields | 20 |
| Demonstrated experience in designing quantitative and qualitative studies, including data analysis, statistical inference, and presentation, including charts and infographics | 10 |
| Experience in known qualitative software and data analysis, and in presenting qualitative data, including diagrams, detailed descriptions and other approaches | 10 |
| Experience with administering education outcomes measurement tools such as EGRA, STAR and EGMA | 20 |
| Prior experience with World Vision or other international NGO assessment of grant funded education projects within the last two – five years in the DRC. | 15 |
| Knowledge and experience of developing country contexts and the education sector | 5 |
| Fluency in French is essential | 5 |
| Preferred research or academic institutions (or affiliates) | 5 |
| Demonstrated ability to produce a high quality report in French and English under tight deadline | 10 |

# Roles and Responsibilities of Evaluation Participants

| Name | Position | Duties | TOR approval required? (Yes/No) | Inception report approval required? (Yes/No) | Final report approval required? (Yes/No) |
| --- | --- | --- | --- | --- | --- |
| Fred Buingo, | NO Project Manager, | Drafting initial TOR Review of Draft reports | No | No | No |
| Philidor Bikengu | NO M&E Coordinator | Drafting initial TOR Review of Draft reports | No | No | No |
| Simon Makono | SRH, MEAL Manager | Drafting initial TOR Review of Draft reports | Yes | Yes | Yes |
| Taonga Banda | NO GAM Manager | Review of draft report Submission of final report to CIM | Yes | Yes | Yes |
|  | NO Project Staff (add lines as required) | Mobilisation of participants Interviewee | No | No | No |
|  | NO Supply Chain Manager | Evaluation of Bids/Selection of consultant Contracting Management of consultant | No | No | No |
| Betty Malu Dady Mukeba | NO Safeguarding Manager | Ensure adherence to Safeguarding policy | No | No | No |
|  | NO QA Director | Final Approval | No | No | Yes |
|  | NO GAM Director | Final Review Final Approval |  |  | Yes |
|  | Finance Manager | Ensure payment as per policies | No | No | No |
|  | NO (EPST / partner Proved, Sous Proved, IPP, Inspool) | Interviewee | No | No | No |
|  | NO (School Principals, Inspectors/ partner) | Interviewee | No | No | No |
|  | CRS (Principals, Inspectors) | Interviewee | No | No | No |
|  | DIVAS, DIGENRE | Interviewee | No | No | No |
|  | AHADI | Interviewee | No | No | No |
| Kathryn Delahunty | WVA CIM |  | Yes | Yes | Yes |
| Viktoria Midelauri | WVA Disability and Education Advisor | Review of ToR, inception report, report drafts | No | No | No |
|  | DFAT Post (add lines as required) |  |  |  |  |

# Assignment Conditions

The assignment is expected to be awarded in country (DRC) and the successful consultant is expected to have a team within the country to deliver the assignment successfully. World Vision will meet the logistical costs. The consultant is expected to recruit and deploy a team of data collectors as necessary and ensure they are adequately trained to deliver the assignment with the expected quality.

# Limitations

Some issues to consider during this evaluation

- Access to some project locations may be limited due roads destroyed by flooding and landslides or broken bridges but WVDRC will ensure that their local sub-office works on mitigating the effects of this.

- Teacher’s strikes may also happen as this has happened before. WVDRC will take an active interest in updating the consultant on the same and ensuring that there are workable alternative arrangements.

- Demonstration in the project locations – the local security focal person will ensure that this is mitigated, and staff and consultants are safe.

- Political campaigns for upcoming elections and possible unrest following elections

- Participants relocated to other villages

# Schedule and timeframe

| Phase: preparation | Responsible | Due date |
| --- | --- | --- |
| Phase: Bid and Award | World Vision |  |
| Call for Proposals advertised | World Vision | 13 November 2023 |
| Deadline for clarifications | World Vision | 20 November 2023 |
| Receive proposals, | World Vision | 4 December 2023 |
| Evaluation Timeframe i.e. Interview, | World Vision | 15 December 2023 |
| Award of Contract using appropriate procurement practices | World Vision | 10 January 2024 |
| Draft Inception Plan | Consultant | 19 January 2024 |
| Final Inception Plan | Consultant | 26 January 2024 |
| Recruitment of data collection team | Consultant | 19 February 2024 |
| Phase: data collection | Consultant | 11 Mar– 10 Ap 2024 |
| Indicator measurement | Consultant |  |
| - Quantitative participant selection | Consultant |  |
| - Quantitative data collection | Consultant |  |
| - Quantitative data analysis and presentation of findings | Consultant |  |
| Learning Lessons | Consultant |  |
| Qualitative participant selection | Consultant |  |
| Qualitative data collection | Consultant |  |
| Qualitative data analysis | Consultant |  |
| Phase: report writing | Consultant |  |
| 1st complete draft report | Consultant | 23 April 2024 |
| Review first draft | World Vision, SRH, Mean manager, PM, MEAL, CIM | 30 April 2024 |
| 2nd draft report, first draft executive summary / impact brief | Consultant | 6 May 2024 |
| Review second draft | World Vision, SRH, Mean manager, PM, MEAL, CIM | 13 May 2024 |
| Final report and executive summary / impact brief | World Vision, SRH, Mean manager, PM, MEAL, CIM | 20 May 2024 |

# Budget

TBA

# Instructions to bidders and evaluation criteria

The interested Consulting firm/Consultant will have to produce both a technical and a financial proposal based on this ToR and submit the same to the National Office as per the guidance below:

- Instructions to interested bidders

- The deadline to submit your bid is set on the 30 November 2023

- Bid should be submitted in English and include the following:

  - Technical offer including the following:

    - Proposed methodology (not exceeding 5 x A4 pages)

    - Detailed proposed workplan

    - CV of the consultant firm (if relevant) (not exceeding 2 x A4 pages)

    - Roles and responsibilities of evaluation team member (including level of effort)

    - Summary CV of evaluation team members detailing similar experience (not exceeding a quarter A4 page per team member)

    - Full CVs in annex (not exceeding 3 x A4 pages per CV)

    - Samples of previous similar pieces of work (not exceeding 2 pieces of work)

    - Contact of references (2 references minimum to be provided)

  - Detailed financial offer in USD currency describing consulting fees, international and national travels, costs of facilitators, transport, travel and accommodation

  - Written confirmation of availability during the indicated timeframe

  - Submit your bid by:  (add submission options here).

- Questions and Answers (optional)

Questions regarding this bid can be asked until the 20th of November and should be addressed to the Supply Chain department.

# Hiring Conditions and contractual requirements

The successful consultant will have to meet all the World Vision International DRC and World Vision Australia procurement requirements. These include and are not limited to, the pre-award background checks (police clearance, blocked party list etc), signing of all child and adult safeguarding policies and undertaking to ensure the observance of the same throughout the process. Relevant documentation will be shared with the successful consultant prior to the final award.

# Reference Documents

Below are the relevant documents for the assignment, which will be shared upon request with the bidders for this opportunity.

- Baseline Report

- MTR Report and Dataset

- Proposal Design Document

- Progress Reports (Semi Annual and Annual)

- Context Reports

- MEAL Documents

The detailed descriptions of the project models and approaches used will be shared with the bidders

www.raosoft.com/samplesite.html.